## README
Sheet | Purpose | How to use
README | Importer guide and workbook structure | Start here. Map Jira fields from the Jira_Import sheet.
Epic_Summary | Epic-level scope, outcomes, and ownership | Use for program tracking and release review.
Sprint_Plan | Sprint-by-sprint sequencing and milestones | Use for roadmap and team planning.
Jira_Import | Ticket backlog in CSV-friendly structure | Import into Jira or copy rows into your existing project.
Dependencies | Cross-epic and cross-sprint dependencies | Use during scrum-of-scrums and release planning.
Acceptance_Notes | Release-level acceptance and done criteria | Use at demo/release gates.

## Epic_Summary
Epic ID | Epic Name | Outcome | Owner Group | Planned Window | Priority
EP-01 | Platform Foundations & DevEx | Repo, standards, CI baseline, environments, secrets, coding conventions. | Platform | Sprint 0-1 | Critical
EP-02 | Identity, Auth & Policy | Tenant auth, workload tokens, RBAC, policy bundles, audit hooks. | Security | Sprint 1-3 | Critical
EP-03 | Control Plane Core | API Gateway, Supervisor, Planner, run lifecycle, run state. | Backend | Sprint 1-4 | Critical
EP-04 | Knowledge Plane | Retrieval, artifact catalog, episodic memory, indexing. | ML Platform | Sprint 2-5 | High
EP-05 | Execution Plane | Swarm scheduling, runtime manager, sandbox executor, result aggregation. | Platform | Sprint 3-6 | Critical
EP-06 | Model & Tool Access | Model gateway, tool broker, usage policy, quota enforcement. | Platform | Sprint 3-6 | Critical
EP-07 | Evaluation & Simulation | Benchmarking, replay, simulation, quality evidence. | ML Eng | Sprint 5-8 | High
EP-08 | Release, Deployment & Environments | Artifact signing, release manager, canary, rollback. | DevOps | Sprint 6-9 | High
EP-09 | Observability & Audit | Metrics, logs, traces, audit ledger, dashboards. | SRE | Sprint 2-8 | Critical
EP-10 | Studio & Workflow UI | Brief builder, architecture compare, evaluation lab, release center. | Frontend | Sprint 4-10 | High
EP-11 | Governance & Executive UX | Approvals, incidents, audit view, executive portfolio. | Frontend | Sprint 8-10 | Medium
EP-12 | Hardening, Performance & Launch | Load tests, threat model remediation, cutover, runbooks. | Cross-functional | Sprint 10-12 | Critical

## Sprint_Plan
Sprint | Theme | Primary Epics | Exit Criteria
Sprint 0 | Program setup | EP-01 | Repo bootstrap, coding standards, CI/CD skeleton, environments, architecture decision records
Sprint 1 | Identity + run bootstrap | EP-02, EP-03 | Tenant auth, token service skeleton, POST /v1/runs, run store
Sprint 2 | Planner + observability baseline | EP-03, EP-09 | Plan generation contract, trace ids, logs/metrics, audit event envelope
Sprint 3 | Execution plane alpha | EP-05, EP-06 | Swarm queueing, runtime manager, tool broker skeleton, model gateway alpha
Sprint 4 | Knowledge plane alpha + Studio foundations | EP-04, EP-10 | Retrieval search, artifact catalog, Brief Builder, basic agent overview UI
Sprint 5 | Evaluation alpha | EP-04, EP-07 | Benchmark harness, replay framework, candidate evaluation endpoint
Sprint 6 | Release flow alpha | EP-05, EP-06, EP-08 | Artifact manifest, signed release candidate flow, release center UI
Sprint 7 | Observability deepening | EP-07, EP-09 | Trace drill-down, alerting, runtime diagnostics, eval evidence views
Sprint 8 | Governance UX and approvals | EP-08, EP-11 | Approval queues, audit surfaces, canary health review
Sprint 9 | Production controls | EP-08, EP-10 | Rollback automation, environment controls, runtime overview hardening
Sprint 10 | Executive layer + non-functional hardening | EP-11, EP-12 | Portfolio dashboard, SLO views, perf and security fixes
Sprint 11 | Beta readiness | EP-12 | Load test closure, runbooks, incident playbooks, release rehearsal
Sprint 12 | Launch and stabilization | EP-12 | GA checklist, support handoff, defect burn-down, post-launch metrics

## Jira_Import
External ID | Issue Type | Summary | Description | Epic Name | Epic Ref | Epic Link | Parent External ID | Priority | Story Points | Sprint | Component | Labels | Depends On | Acceptance Criteria | Owner Role | Fix Version
EP-01 | Epic | Platform Foundations & DevEx | Repo, standards, CI baseline, environments, secrets, coding conventions. | Platform Foundations & DevEx | EP-01 |  |  | Critical |  | Sprint 0-1 | Platform | epic,ep-01 |  | Epic outcome achieved: Repo, standards, CI baseline, environments, secrets, coding conventions. | Platform | Release 1
EP-02 | Epic | Identity, Auth & Policy | Tenant auth, workload tokens, RBAC, policy bundles, audit hooks. | Identity, Auth & Policy | EP-02 |  |  | Critical |  | Sprint 1-3 | Security | epic,ep-02 |  | Epic outcome achieved: Tenant auth, workload tokens, RBAC, policy bundles, audit hooks. | Security | Release 1
EP-03 | Epic | Control Plane Core | API Gateway, Supervisor, Planner, run lifecycle, run state. | Control Plane Core | EP-03 |  |  | Critical |  | Sprint 1-4 | Backend | epic,ep-03 |  | Epic outcome achieved: API Gateway, Supervisor, Planner, run lifecycle, run state. | Backend | Release 1
EP-04 | Epic | Knowledge Plane | Retrieval, artifact catalog, episodic memory, indexing. | Knowledge Plane | EP-04 |  |  | High |  | Sprint 2-5 | ML Platform | epic,ep-04 |  | Epic outcome achieved: Retrieval, artifact catalog, episodic memory, indexing. | ML Platform | Release 1
EP-05 | Epic | Execution Plane | Swarm scheduling, runtime manager, sandbox executor, result aggregation. | Execution Plane | EP-05 |  |  | Critical |  | Sprint 3-6 | Platform | epic,ep-05 |  | Epic outcome achieved: Swarm scheduling, runtime manager, sandbox executor, result aggregation. | Platform | Release 1
EP-06 | Epic | Model & Tool Access | Model gateway, tool broker, usage policy, quota enforcement. | Model & Tool Access | EP-06 |  |  | Critical |  | Sprint 3-6 | Platform | epic,ep-06 |  | Epic outcome achieved: Model gateway, tool broker, usage policy, quota enforcement. | Platform | Release 1
EP-07 | Epic | Evaluation & Simulation | Benchmarking, replay, simulation, quality evidence. | Evaluation & Simulation | EP-07 |  |  | High |  | Sprint 5-8 | ML Eng | epic,ep-07 |  | Epic outcome achieved: Benchmarking, replay, simulation, quality evidence. | ML Eng | Release 1
EP-08 | Epic | Release, Deployment & Environments | Artifact signing, release manager, canary, rollback. | Release, Deployment & Environments | EP-08 |  |  | High |  | Sprint 6-9 | DevOps | epic,ep-08 |  | Epic outcome achieved: Artifact signing, release manager, canary, rollback. | DevOps | Release 1
EP-09 | Epic | Observability & Audit | Metrics, logs, traces, audit ledger, dashboards. | Observability & Audit | EP-09 |  |  | Critical |  | Sprint 2-8 | SRE | epic,ep-09 |  | Epic outcome achieved: Metrics, logs, traces, audit ledger, dashboards. | SRE | Release 1
EP-10 | Epic | Studio & Workflow UI | Brief builder, architecture compare, evaluation lab, release center. | Studio & Workflow UI | EP-10 |  |  | High |  | Sprint 4-10 | Frontend | epic,ep-10 |  | Epic outcome achieved: Brief builder, architecture compare, evaluation lab, release center. | Frontend | Release 1
EP-11 | Epic | Governance & Executive UX | Approvals, incidents, audit view, executive portfolio. | Governance & Executive UX | EP-11 |  |  | Medium |  | Sprint 8-10 | Frontend | epic,ep-11 |  | Epic outcome achieved: Approvals, incidents, audit view, executive portfolio. | Frontend | Release 1
EP-12 | Epic | Hardening, Performance & Launch | Load tests, threat model remediation, cutover, runbooks. | Hardening, Performance & Launch | EP-12 |  |  | Critical |  | Sprint 10-12 | Cross-functional | epic,ep-12 |  | Epic outcome achieved: Load tests, threat model remediation, cutover, runbooks. | Cross-functional | Release 1
EP-01-ST-01 | Story | Platform Foundations & DevEx: Define contract and ADRs | Create detailed contracts, ADRs, and coding conventions for the area. |  | EP-01 | EP-01 |  | Critical | 3 | Sprint 0 | Platform | story,ep-01,platform |  | Given Platform Foundations & DevEx, when define contract and adrs, then the deliverable is reviewed, tested, and demoable against the contract pack. | Tech Lead | Release 1
EP-01-ST-02 | Story | Platform Foundations & DevEx: Implement service skeleton | Create service repository/module, health checks, config, and CI integration. |  | EP-01 | EP-01 |  | Critical | 5 | Sprint 0 | Platform | story,ep-01,platform |  | Given Platform Foundations & DevEx, when implement service skeleton, then the deliverable is reviewed, tested, and demoable against the contract pack. | Tech Lead | Release 1
EP-01-ST-03 | Story | Platform Foundations & DevEx: Implement primary endpoint or worker flow | Deliver the main functional path with tests and tracing. |  | EP-01 | EP-01 |  | Critical | 8 | Sprint 0 | Platform | story,ep-01,platform |  | Given Platform Foundations & DevEx, when implement primary endpoint or worker flow, then the deliverable is reviewed, tested, and demoable against the contract pack. | Tech Lead | Release 1
EP-01-ST-04 | Story | Platform Foundations & DevEx: Add policy, validation, and error handling | Add guardrails, validation, and standard error envelope behavior. |  | EP-01 | EP-01 |  | Critical | 5 | Sprint 0 | Platform | story,ep-01,platform |  | Given Platform Foundations & DevEx, when add policy, validation, and error handling, then the deliverable is reviewed, tested, and demoable against the contract pack. | Tech Lead | Release 1
EP-01-ST-05 | Story | Platform Foundations & DevEx: Add observability and audit hooks | Emit logs, traces, metrics, and audit events for the area. |  | EP-01 | EP-01 |  | Critical | 3 | Sprint 0 | Platform | story,ep-01,platform |  | Given Platform Foundations & DevEx, when add observability and audit hooks, then the deliverable is reviewed, tested, and demoable against the contract pack. | Tech Lead | Release 1
EP-01-ST-06 | Story | Platform Foundations & DevEx: Integration and demo readiness | Integrate with dependent services and provide demo evidence. |  | EP-01 | EP-01 |  | Critical | 5 | Sprint 0 | Platform | story,ep-01,platform |  | Given Platform Foundations & DevEx, when integration and demo readiness, then the deliverable is reviewed, tested, and demoable against the contract pack. | Tech Lead | Release 1
EP-01-TS-01 | Task | Platform Foundations & DevEx: Test automation | Add unit, integration, and contract tests. |  | EP-01 | EP-01 | EP-01-ST-03 | High | 3 | Sprint 0 | Platform | task,qa,ep-01 | EP-01-ST-03 | Automated tests pass in CI for the scoped area. | QA Engineer | Release 1
EP-01-TS-02 | Task | Platform Foundations & DevEx: Documentation | Write service README, runbook, and handoff notes. |  | EP-01 | EP-01 | EP-01-ST-03 | Medium | 2 | Sprint 0 | Platform | task,docs,ep-01 | EP-01-ST-03 | Documentation is complete and reviewed. | Tech Writer | Release 1
EP-02-ST-01 | Story | Identity, Auth & Policy: Define contract and ADRs | Create detailed contracts, ADRs, and coding conventions for the area. |  | EP-02 | EP-02 |  | Critical | 3 | Sprint 1 | Security | story,ep-02,security | EP-01 | Given Identity, Auth & Policy, when define contract and adrs, then the deliverable is reviewed, tested, and demoable against the contract pack. | Security Engineer | Release 1
EP-02-ST-02 | Story | Identity, Auth & Policy: Implement service skeleton | Create service repository/module, health checks, config, and CI integration. |  | EP-02 | EP-02 |  | Critical | 5 | Sprint 1 | Security | story,ep-02,security | EP-01 | Given Identity, Auth & Policy, when implement service skeleton, then the deliverable is reviewed, tested, and demoable against the contract pack. | Security Engineer | Release 1
EP-02-ST-03 | Story | Identity, Auth & Policy: Implement primary endpoint or worker flow | Deliver the main functional path with tests and tracing. |  | EP-02 | EP-02 |  | Critical | 8 | Sprint 1 | Security | story,ep-02,security | EP-01 | Given Identity, Auth & Policy, when implement primary endpoint or worker flow, then the deliverable is reviewed, tested, and demoable against the contract pack. | Security Engineer | Release 1
EP-02-ST-04 | Story | Identity, Auth & Policy: Add policy, validation, and error handling | Add guardrails, validation, and standard error envelope behavior. |  | EP-02 | EP-02 |  | Critical | 5 | Sprint 1 | Security | story,ep-02,security | EP-01 | Given Identity, Auth & Policy, when add policy, validation, and error handling, then the deliverable is reviewed, tested, and demoable against the contract pack. | Security Engineer | Release 1
EP-02-ST-05 | Story | Identity, Auth & Policy: Add observability and audit hooks | Emit logs, traces, metrics, and audit events for the area. |  | EP-02 | EP-02 |  | Critical | 3 | Sprint 1 | Security | story,ep-02,security | EP-01 | Given Identity, Auth & Policy, when add observability and audit hooks, then the deliverable is reviewed, tested, and demoable against the contract pack. | Security Engineer | Release 1
EP-02-ST-06 | Story | Identity, Auth & Policy: Integration and demo readiness | Integrate with dependent services and provide demo evidence. |  | EP-02 | EP-02 |  | Critical | 5 | Sprint 1 | Security | story,ep-02,security | EP-01 | Given Identity, Auth & Policy, when integration and demo readiness, then the deliverable is reviewed, tested, and demoable against the contract pack. | Security Engineer | Release 1
EP-02-TS-01 | Task | Identity, Auth & Policy: Test automation | Add unit, integration, and contract tests. |  | EP-02 | EP-02 | EP-02-ST-03 | High | 3 | Sprint 1 | Security | task,qa,ep-02 | EP-02-ST-03 | Automated tests pass in CI for the scoped area. | QA Engineer | Release 1
EP-02-TS-02 | Task | Identity, Auth & Policy: Documentation | Write service README, runbook, and handoff notes. |  | EP-02 | EP-02 | EP-02-ST-03 | Medium | 2 | Sprint 1 | Security | task,docs,ep-02 | EP-02-ST-03 | Documentation is complete and reviewed. | Tech Writer | Release 1
EP-03-ST-01 | Story | Control Plane Core: Define contract and ADRs | Create detailed contracts, ADRs, and coding conventions for the area. |  | EP-03 | EP-03 |  | Critical | 3 | Sprint 1 | ControlPlane | story,ep-03,controlplane | EP-01 | Given Control Plane Core, when define contract and adrs, then the deliverable is reviewed, tested, and demoable against the contract pack. | Backend Engineer | Release 1
EP-03-ST-02 | Story | Control Plane Core: Implement service skeleton | Create service repository/module, health checks, config, and CI integration. |  | EP-03 | EP-03 |  | Critical | 5 | Sprint 1 | ControlPlane | story,ep-03,controlplane | EP-01 | Given Control Plane Core, when implement service skeleton, then the deliverable is reviewed, tested, and demoable against the contract pack. | Backend Engineer | Release 1
EP-03-ST-03 | Story | Control Plane Core: Implement primary endpoint or worker flow | Deliver the main functional path with tests and tracing. |  | EP-03 | EP-03 |  | Critical | 8 | Sprint 1 | ControlPlane | story,ep-03,controlplane | EP-01 | Given Control Plane Core, when implement primary endpoint or worker flow, then the deliverable is reviewed, tested, and demoable against the contract pack. | Backend Engineer | Release 1
EP-03-ST-04 | Story | Control Plane Core: Add policy, validation, and error handling | Add guardrails, validation, and standard error envelope behavior. |  | EP-03 | EP-03 |  | Critical | 5 | Sprint 1 | ControlPlane | story,ep-03,controlplane | EP-01 | Given Control Plane Core, when add policy, validation, and error handling, then the deliverable is reviewed, tested, and demoable against the contract pack. | Backend Engineer | Release 1
EP-03-ST-05 | Story | Control Plane Core: Add observability and audit hooks | Emit logs, traces, metrics, and audit events for the area. |  | EP-03 | EP-03 |  | Critical | 3 | Sprint 1 | ControlPlane | story,ep-03,controlplane | EP-01 | Given Control Plane Core, when add observability and audit hooks, then the deliverable is reviewed, tested, and demoable against the contract pack. | Backend Engineer | Release 1
EP-03-ST-06 | Story | Control Plane Core: Integration and demo readiness | Integrate with dependent services and provide demo evidence. |  | EP-03 | EP-03 |  | Critical | 5 | Sprint 1 | ControlPlane | story,ep-03,controlplane | EP-01 | Given Control Plane Core, when integration and demo readiness, then the deliverable is reviewed, tested, and demoable against the contract pack. | Backend Engineer | Release 1
EP-03-TS-01 | Task | Control Plane Core: Test automation | Add unit, integration, and contract tests. |  | EP-03 | EP-03 | EP-03-ST-03 | High | 3 | Sprint 1 | ControlPlane | task,qa,ep-03 | EP-03-ST-03 | Automated tests pass in CI for the scoped area. | QA Engineer | Release 1
EP-03-TS-02 | Task | Control Plane Core: Documentation | Write service README, runbook, and handoff notes. |  | EP-03 | EP-03 | EP-03-ST-03 | Medium | 2 | Sprint 1 | ControlPlane | task,docs,ep-03 | EP-03-ST-03 | Documentation is complete and reviewed. | Tech Writer | Release 1
EP-04-ST-01 | Story | Knowledge Plane: Define contract and ADRs | Create detailed contracts, ADRs, and coding conventions for the area. |  | EP-04 | EP-04 |  | High | 3 | Sprint 4 | Knowledge | story,ep-04,knowledge | EP-03 | Given Knowledge Plane, when define contract and adrs, then the deliverable is reviewed, tested, and demoable against the contract pack. | ML Engineer | Release 1
EP-04-ST-02 | Story | Knowledge Plane: Implement service skeleton | Create service repository/module, health checks, config, and CI integration. |  | EP-04 | EP-04 |  | High | 5 | Sprint 4 | Knowledge | story,ep-04,knowledge | EP-03 | Given Knowledge Plane, when implement service skeleton, then the deliverable is reviewed, tested, and demoable against the contract pack. | ML Engineer | Release 1
EP-04-ST-03 | Story | Knowledge Plane: Implement primary endpoint or worker flow | Deliver the main functional path with tests and tracing. |  | EP-04 | EP-04 |  | High | 8 | Sprint 4 | Knowledge | story,ep-04,knowledge | EP-03 | Given Knowledge Plane, when implement primary endpoint or worker flow, then the deliverable is reviewed, tested, and demoable against the contract pack. | ML Engineer | Release 1
EP-04-ST-04 | Story | Knowledge Plane: Add policy, validation, and error handling | Add guardrails, validation, and standard error envelope behavior. |  | EP-04 | EP-04 |  | High | 5 | Sprint 4 | Knowledge | story,ep-04,knowledge | EP-03 | Given Knowledge Plane, when add policy, validation, and error handling, then the deliverable is reviewed, tested, and demoable against the contract pack. | ML Engineer | Release 1
EP-04-ST-05 | Story | Knowledge Plane: Add observability and audit hooks | Emit logs, traces, metrics, and audit events for the area. |  | EP-04 | EP-04 |  | High | 3 | Sprint 4 | Knowledge | story,ep-04,knowledge | EP-03 | Given Knowledge Plane, when add observability and audit hooks, then the deliverable is reviewed, tested, and demoable against the contract pack. | ML Engineer | Release 1
EP-04-ST-06 | Story | Knowledge Plane: Integration and demo readiness | Integrate with dependent services and provide demo evidence. |  | EP-04 | EP-04 |  | High | 5 | Sprint 4 | Knowledge | story,ep-04,knowledge | EP-03 | Given Knowledge Plane, when integration and demo readiness, then the deliverable is reviewed, tested, and demoable against the contract pack. | ML Engineer | Release 1
EP-04-TS-01 | Task | Knowledge Plane: Test automation | Add unit, integration, and contract tests. |  | EP-04 | EP-04 | EP-04-ST-03 | High | 3 | Sprint 4 | Knowledge | task,qa,ep-04 | EP-04-ST-03 | Automated tests pass in CI for the scoped area. | QA Engineer | Release 1
EP-04-TS-02 | Task | Knowledge Plane: Documentation | Write service README, runbook, and handoff notes. |  | EP-04 | EP-04 | EP-04-ST-03 | Medium | 2 | Sprint 4 | Knowledge | task,docs,ep-04 | EP-04-ST-03 | Documentation is complete and reviewed. | Tech Writer | Release 1
EP-05-ST-01 | Story | Execution Plane: Define contract and ADRs | Create detailed contracts, ADRs, and coding conventions for the area. |  | EP-05 | EP-05 |  | Critical | 3 | Sprint 3 | Execution | story,ep-05,execution | EP-03 | Given Execution Plane, when define contract and adrs, then the deliverable is reviewed, tested, and demoable against the contract pack. | Platform Engineer | Release 1
EP-05-ST-02 | Story | Execution Plane: Implement service skeleton | Create service repository/module, health checks, config, and CI integration. |  | EP-05 | EP-05 |  | Critical | 5 | Sprint 3 | Execution | story,ep-05,execution | EP-03 | Given Execution Plane, when implement service skeleton, then the deliverable is reviewed, tested, and demoable against the contract pack. | Platform Engineer | Release 1
EP-05-ST-03 | Story | Execution Plane: Implement primary endpoint or worker flow | Deliver the main functional path with tests and tracing. |  | EP-05 | EP-05 |  | Critical | 8 | Sprint 3 | Execution | story,ep-05,execution | EP-03 | Given Execution Plane, when implement primary endpoint or worker flow, then the deliverable is reviewed, tested, and demoable against the contract pack. | Platform Engineer | Release 1
EP-05-ST-04 | Story | Execution Plane: Add policy, validation, and error handling | Add guardrails, validation, and standard error envelope behavior. |  | EP-05 | EP-05 |  | Critical | 5 | Sprint 3 | Execution | story,ep-05,execution | EP-03 | Given Execution Plane, when add policy, validation, and error handling, then the deliverable is reviewed, tested, and demoable against the contract pack. | Platform Engineer | Release 1
EP-05-ST-05 | Story | Execution Plane: Add observability and audit hooks | Emit logs, traces, metrics, and audit events for the area. |  | EP-05 | EP-05 |  | Critical | 3 | Sprint 3 | Execution | story,ep-05,execution | EP-03 | Given Execution Plane, when add observability and audit hooks, then the deliverable is reviewed, tested, and demoable against the contract pack. | Platform Engineer | Release 1
EP-05-ST-06 | Story | Execution Plane: Integration and demo readiness | Integrate with dependent services and provide demo evidence. |  | EP-05 | EP-05 |  | Critical | 5 | Sprint 3 | Execution | story,ep-05,execution | EP-03 | Given Execution Plane, when integration and demo readiness, then the deliverable is reviewed, tested, and demoable against the contract pack. | Platform Engineer | Release 1
EP-05-TS-01 | Task | Execution Plane: Test automation | Add unit, integration, and contract tests. |  | EP-05 | EP-05 | EP-05-ST-03 | High | 3 | Sprint 3 | Execution | task,qa,ep-05 | EP-05-ST-03 | Automated tests pass in CI for the scoped area. | QA Engineer | Release 1
EP-05-TS-02 | Task | Execution Plane: Documentation | Write service README, runbook, and handoff notes. |  | EP-05 | EP-05 | EP-05-ST-03 | Medium | 2 | Sprint 3 | Execution | task,docs,ep-05 | EP-05-ST-03 | Documentation is complete and reviewed. | Tech Writer | Release 1
EP-06-ST-01 | Story | Model & Tool Access: Define contract and ADRs | Create detailed contracts, ADRs, and coding conventions for the area. |  | EP-06 | EP-06 |  | Critical | 3 | Sprint 3 | ModelTool | story,ep-06,modeltool | EP-02 | Given Model & Tool Access, when define contract and adrs, then the deliverable is reviewed, tested, and demoable against the contract pack. | Platform Engineer | Release 1
EP-06-ST-02 | Story | Model & Tool Access: Implement service skeleton | Create service repository/module, health checks, config, and CI integration. |  | EP-06 | EP-06 |  | Critical | 5 | Sprint 3 | ModelTool | story,ep-06,modeltool | EP-02 | Given Model & Tool Access, when implement service skeleton, then the deliverable is reviewed, tested, and demoable against the contract pack. | Platform Engineer | Release 1
EP-06-ST-03 | Story | Model & Tool Access: Implement primary endpoint or worker flow | Deliver the main functional path with tests and tracing. |  | EP-06 | EP-06 |  | Critical | 8 | Sprint 3 | ModelTool | story,ep-06,modeltool | EP-02 | Given Model & Tool Access, when implement primary endpoint or worker flow, then the deliverable is reviewed, tested, and demoable against the contract pack. | Platform Engineer | Release 1
EP-06-ST-04 | Story | Model & Tool Access: Add policy, validation, and error handling | Add guardrails, validation, and standard error envelope behavior. |  | EP-06 | EP-06 |  | Critical | 5 | Sprint 3 | ModelTool | story,ep-06,modeltool | EP-02 | Given Model & Tool Access, when add policy, validation, and error handling, then the deliverable is reviewed, tested, and demoable against the contract pack. | Platform Engineer | Release 1
EP-06-ST-05 | Story | Model & Tool Access: Add observability and audit hooks | Emit logs, traces, metrics, and audit events for the area. |  | EP-06 | EP-06 |  | Critical | 3 | Sprint 3 | ModelTool | story,ep-06,modeltool | EP-02 | Given Model & Tool Access, when add observability and audit hooks, then the deliverable is reviewed, tested, and demoable against the contract pack. | Platform Engineer | Release 1
EP-06-ST-06 | Story | Model & Tool Access: Integration and demo readiness | Integrate with dependent services and provide demo evidence. |  | EP-06 | EP-06 |  | Critical | 5 | Sprint 3 | ModelTool | story,ep-06,modeltool | EP-02 | Given Model & Tool Access, when integration and demo readiness, then the deliverable is reviewed, tested, and demoable against the contract pack. | Platform Engineer | Release 1
EP-06-TS-01 | Task | Model & Tool Access: Test automation | Add unit, integration, and contract tests. |  | EP-06 | EP-06 | EP-06-ST-03 | High | 3 | Sprint 3 | ModelTool | task,qa,ep-06 | EP-06-ST-03 | Automated tests pass in CI for the scoped area. | QA Engineer | Release 1
EP-06-TS-02 | Task | Model & Tool Access: Documentation | Write service README, runbook, and handoff notes. |  | EP-06 | EP-06 | EP-06-ST-03 | Medium | 2 | Sprint 3 | ModelTool | task,docs,ep-06 | EP-06-ST-03 | Documentation is complete and reviewed. | Tech Writer | Release 1
EP-07-ST-01 | Story | Evaluation & Simulation: Define contract and ADRs | Create detailed contracts, ADRs, and coding conventions for the area. |  | EP-07 | EP-07 |  | High | 3 | Sprint 5 | Evaluation | story,ep-07,evaluation | EP-04 | Given Evaluation & Simulation, when define contract and adrs, then the deliverable is reviewed, tested, and demoable against the contract pack. | ML Engineer | Release 1
EP-07-ST-02 | Story | Evaluation & Simulation: Implement service skeleton | Create service repository/module, health checks, config, and CI integration. |  | EP-07 | EP-07 |  | High | 5 | Sprint 5 | Evaluation | story,ep-07,evaluation | EP-04 | Given Evaluation & Simulation, when implement service skeleton, then the deliverable is reviewed, tested, and demoable against the contract pack. | ML Engineer | Release 1
EP-07-ST-03 | Story | Evaluation & Simulation: Implement primary endpoint or worker flow | Deliver the main functional path with tests and tracing. |  | EP-07 | EP-07 |  | High | 8 | Sprint 5 | Evaluation | story,ep-07,evaluation | EP-04 | Given Evaluation & Simulation, when implement primary endpoint or worker flow, then the deliverable is reviewed, tested, and demoable against the contract pack. | ML Engineer | Release 1
EP-07-ST-04 | Story | Evaluation & Simulation: Add policy, validation, and error handling | Add guardrails, validation, and standard error envelope behavior. |  | EP-07 | EP-07 |  | High | 5 | Sprint 5 | Evaluation | story,ep-07,evaluation | EP-04 | Given Evaluation & Simulation, when add policy, validation, and error handling, then the deliverable is reviewed, tested, and demoable against the contract pack. | ML Engineer | Release 1
EP-07-ST-05 | Story | Evaluation & Simulation: Add observability and audit hooks | Emit logs, traces, metrics, and audit events for the area. |  | EP-07 | EP-07 |  | High | 3 | Sprint 5 | Evaluation | story,ep-07,evaluation | EP-04 | Given Evaluation & Simulation, when add observability and audit hooks, then the deliverable is reviewed, tested, and demoable against the contract pack. | ML Engineer | Release 1
EP-07-ST-06 | Story | Evaluation & Simulation: Integration and demo readiness | Integrate with dependent services and provide demo evidence. |  | EP-07 | EP-07 |  | High | 5 | Sprint 5 | Evaluation | story,ep-07,evaluation | EP-04 | Given Evaluation & Simulation, when integration and demo readiness, then the deliverable is reviewed, tested, and demoable against the contract pack. | ML Engineer | Release 1
EP-07-TS-01 | Task | Evaluation & Simulation: Test automation | Add unit, integration, and contract tests. |  | EP-07 | EP-07 | EP-07-ST-03 | High | 3 | Sprint 5 | Evaluation | task,qa,ep-07 | EP-07-ST-03 | Automated tests pass in CI for the scoped area. | QA Engineer | Release 1
EP-07-TS-02 | Task | Evaluation & Simulation: Documentation | Write service README, runbook, and handoff notes. |  | EP-07 | EP-07 | EP-07-ST-03 | Medium | 2 | Sprint 5 | Evaluation | task,docs,ep-07 | EP-07-ST-03 | Documentation is complete and reviewed. | Tech Writer | Release 1
EP-08-ST-01 | Story | Release, Deployment & Environments: Define contract and ADRs | Create detailed contracts, ADRs, and coding conventions for the area. |  | EP-08 | EP-08 |  | High | 3 | Sprint 6 | Release | story,ep-08,release | EP-05 | Given Release, Deployment & Environments, when define contract and adrs, then the deliverable is reviewed, tested, and demoable against the contract pack. | DevOps Engineer | Release 1
EP-08-ST-02 | Story | Release, Deployment & Environments: Implement service skeleton | Create service repository/module, health checks, config, and CI integration. |  | EP-08 | EP-08 |  | High | 5 | Sprint 6 | Release | story,ep-08,release | EP-05 | Given Release, Deployment & Environments, when implement service skeleton, then the deliverable is reviewed, tested, and demoable against the contract pack. | DevOps Engineer | Release 1
EP-08-ST-03 | Story | Release, Deployment & Environments: Implement primary endpoint or worker flow | Deliver the main functional path with tests and tracing. |  | EP-08 | EP-08 |  | High | 8 | Sprint 6 | Release | story,ep-08,release | EP-05 | Given Release, Deployment & Environments, when implement primary endpoint or worker flow, then the deliverable is reviewed, tested, and demoable against the contract pack. | DevOps Engineer | Release 1
EP-08-ST-04 | Story | Release, Deployment & Environments: Add policy, validation, and error handling | Add guardrails, validation, and standard error envelope behavior. |  | EP-08 | EP-08 |  | High | 5 | Sprint 6 | Release | story,ep-08,release | EP-05 | Given Release, Deployment & Environments, when add policy, validation, and error handling, then the deliverable is reviewed, tested, and demoable against the contract pack. | DevOps Engineer | Release 1
EP-08-ST-05 | Story | Release, Deployment & Environments: Add observability and audit hooks | Emit logs, traces, metrics, and audit events for the area. |  | EP-08 | EP-08 |  | High | 3 | Sprint 6 | Release | story,ep-08,release | EP-05 | Given Release, Deployment & Environments, when add observability and audit hooks, then the deliverable is reviewed, tested, and demoable against the contract pack. | DevOps Engineer | Release 1
EP-08-ST-06 | Story | Release, Deployment & Environments: Integration and demo readiness | Integrate with dependent services and provide demo evidence. |  | EP-08 | EP-08 |  | High | 5 | Sprint 6 | Release | story,ep-08,release | EP-05 | Given Release, Deployment & Environments, when integration and demo readiness, then the deliverable is reviewed, tested, and demoable against the contract pack. | DevOps Engineer | Release 1
EP-08-TS-01 | Task | Release, Deployment & Environments: Test automation | Add unit, integration, and contract tests. |  | EP-08 | EP-08 | EP-08-ST-03 | High | 3 | Sprint 6 | Release | task,qa,ep-08 | EP-08-ST-03 | Automated tests pass in CI for the scoped area. | QA Engineer | Release 1
EP-08-TS-02 | Task | Release, Deployment & Environments: Documentation | Write service README, runbook, and handoff notes. |  | EP-08 | EP-08 | EP-08-ST-03 | Medium | 2 | Sprint 6 | Release | task,docs,ep-08 | EP-08-ST-03 | Documentation is complete and reviewed. | Tech Writer | Release 1
EP-09-ST-01 | Story | Observability & Audit: Define contract and ADRs | Create detailed contracts, ADRs, and coding conventions for the area. |  | EP-09 | EP-09 |  | Critical | 3 | Sprint 2 | Observability | story,ep-09,observability | EP-03 | Given Observability & Audit, when define contract and adrs, then the deliverable is reviewed, tested, and demoable against the contract pack. | SRE | Release 1
EP-09-ST-02 | Story | Observability & Audit: Implement service skeleton | Create service repository/module, health checks, config, and CI integration. |  | EP-09 | EP-09 |  | Critical | 5 | Sprint 2 | Observability | story,ep-09,observability | EP-03 | Given Observability & Audit, when implement service skeleton, then the deliverable is reviewed, tested, and demoable against the contract pack. | SRE | Release 1
EP-09-ST-03 | Story | Observability & Audit: Implement primary endpoint or worker flow | Deliver the main functional path with tests and tracing. |  | EP-09 | EP-09 |  | Critical | 8 | Sprint 2 | Observability | story,ep-09,observability | EP-03 | Given Observability & Audit, when implement primary endpoint or worker flow, then the deliverable is reviewed, tested, and demoable against the contract pack. | SRE | Release 1
EP-09-ST-04 | Story | Observability & Audit: Add policy, validation, and error handling | Add guardrails, validation, and standard error envelope behavior. |  | EP-09 | EP-09 |  | Critical | 5 | Sprint 2 | Observability | story,ep-09,observability | EP-03 | Given Observability & Audit, when add policy, validation, and error handling, then the deliverable is reviewed, tested, and demoable against the contract pack. | SRE | Release 1
EP-09-ST-05 | Story | Observability & Audit: Add observability and audit hooks | Emit logs, traces, metrics, and audit events for the area. |  | EP-09 | EP-09 |  | Critical | 3 | Sprint 2 | Observability | story,ep-09,observability | EP-03 | Given Observability & Audit, when add observability and audit hooks, then the deliverable is reviewed, tested, and demoable against the contract pack. | SRE | Release 1
EP-09-ST-06 | Story | Observability & Audit: Integration and demo readiness | Integrate with dependent services and provide demo evidence. |  | EP-09 | EP-09 |  | Critical | 5 | Sprint 2 | Observability | story,ep-09,observability | EP-03 | Given Observability & Audit, when integration and demo readiness, then the deliverable is reviewed, tested, and demoable against the contract pack. | SRE | Release 1
EP-09-TS-01 | Task | Observability & Audit: Test automation | Add unit, integration, and contract tests. |  | EP-09 | EP-09 | EP-09-ST-03 | High | 3 | Sprint 2 | Observability | task,qa,ep-09 | EP-09-ST-03 | Automated tests pass in CI for the scoped area. | QA Engineer | Release 1
EP-09-TS-02 | Task | Observability & Audit: Documentation | Write service README, runbook, and handoff notes. |  | EP-09 | EP-09 | EP-09-ST-03 | Medium | 2 | Sprint 2 | Observability | task,docs,ep-09 | EP-09-ST-03 | Documentation is complete and reviewed. | Tech Writer | Release 1
EP-10-ST-01 | Story | Studio & Workflow UI: Define contract and ADRs | Create detailed contracts, ADRs, and coding conventions for the area. |  | EP-10 | EP-10 |  | High | 3 | Sprint 4 | Frontend | story,ep-10,frontend | EP-03 | Given Studio & Workflow UI, when define contract and adrs, then the deliverable is reviewed, tested, and demoable against the contract pack. | Frontend Engineer | Release 1
EP-10-ST-02 | Story | Studio & Workflow UI: Implement service skeleton | Create service repository/module, health checks, config, and CI integration. |  | EP-10 | EP-10 |  | High | 5 | Sprint 4 | Frontend | story,ep-10,frontend | EP-03 | Given Studio & Workflow UI, when implement service skeleton, then the deliverable is reviewed, tested, and demoable against the contract pack. | Frontend Engineer | Release 1
EP-10-ST-03 | Story | Studio & Workflow UI: Implement primary endpoint or worker flow | Deliver the main functional path with tests and tracing. |  | EP-10 | EP-10 |  | High | 8 | Sprint 4 | Frontend | story,ep-10,frontend | EP-03 | Given Studio & Workflow UI, when implement primary endpoint or worker flow, then the deliverable is reviewed, tested, and demoable against the contract pack. | Frontend Engineer | Release 1
EP-10-ST-04 | Story | Studio & Workflow UI: Add policy, validation, and error handling | Add guardrails, validation, and standard error envelope behavior. |  | EP-10 | EP-10 |  | High | 5 | Sprint 4 | Frontend | story,ep-10,frontend | EP-03 | Given Studio & Workflow UI, when add policy, validation, and error handling, then the deliverable is reviewed, tested, and demoable against the contract pack. | Frontend Engineer | Release 1
EP-10-ST-05 | Story | Studio & Workflow UI: Add observability and audit hooks | Emit logs, traces, metrics, and audit events for the area. |  | EP-10 | EP-10 |  | High | 3 | Sprint 4 | Frontend | story,ep-10,frontend | EP-03 | Given Studio & Workflow UI, when add observability and audit hooks, then the deliverable is reviewed, tested, and demoable against the contract pack. | Frontend Engineer | Release 1
EP-10-ST-06 | Story | Studio & Workflow UI: Integration and demo readiness | Integrate with dependent services and provide demo evidence. |  | EP-10 | EP-10 |  | High | 5 | Sprint 4 | Frontend | story,ep-10,frontend | EP-03 | Given Studio & Workflow UI, when integration and demo readiness, then the deliverable is reviewed, tested, and demoable against the contract pack. | Frontend Engineer | Release 1
EP-10-TS-01 | Task | Studio & Workflow UI: Test automation | Add unit, integration, and contract tests. |  | EP-10 | EP-10 | EP-10-ST-03 | High | 3 | Sprint 4 | Frontend | task,qa,ep-10 | EP-10-ST-03 | Automated tests pass in CI for the scoped area. | QA Engineer | Release 1
EP-10-TS-02 | Task | Studio & Workflow UI: Documentation | Write service README, runbook, and handoff notes. |  | EP-10 | EP-10 | EP-10-ST-03 | Medium | 2 | Sprint 4 | Frontend | task,docs,ep-10 | EP-10-ST-03 | Documentation is complete and reviewed. | Tech Writer | Release 1
EP-11-ST-01 | Story | Governance & Executive UX: Define contract and ADRs | Create detailed contracts, ADRs, and coding conventions for the area. |  | EP-11 | EP-11 |  | Medium | 3 | Sprint 8 | GovernanceUI | story,ep-11,governanceui | EP-09 | Given Governance & Executive UX, when define contract and adrs, then the deliverable is reviewed, tested, and demoable against the contract pack. | Frontend Engineer | Release 1
EP-11-ST-02 | Story | Governance & Executive UX: Implement service skeleton | Create service repository/module, health checks, config, and CI integration. |  | EP-11 | EP-11 |  | Medium | 5 | Sprint 8 | GovernanceUI | story,ep-11,governanceui | EP-09 | Given Governance & Executive UX, when implement service skeleton, then the deliverable is reviewed, tested, and demoable against the contract pack. | Frontend Engineer | Release 1
EP-11-ST-03 | Story | Governance & Executive UX: Implement primary endpoint or worker flow | Deliver the main functional path with tests and tracing. |  | EP-11 | EP-11 |  | Medium | 8 | Sprint 8 | GovernanceUI | story,ep-11,governanceui | EP-09 | Given Governance & Executive UX, when implement primary endpoint or worker flow, then the deliverable is reviewed, tested, and demoable against the contract pack. | Frontend Engineer | Release 1
EP-11-ST-04 | Story | Governance & Executive UX: Add policy, validation, and error handling | Add guardrails, validation, and standard error envelope behavior. |  | EP-11 | EP-11 |  | Medium | 5 | Sprint 8 | GovernanceUI | story,ep-11,governanceui | EP-09 | Given Governance & Executive UX, when add policy, validation, and error handling, then the deliverable is reviewed, tested, and demoable against the contract pack. | Frontend Engineer | Release 1
EP-11-ST-05 | Story | Governance & Executive UX: Add observability and audit hooks | Emit logs, traces, metrics, and audit events for the area. |  | EP-11 | EP-11 |  | Medium | 3 | Sprint 8 | GovernanceUI | story,ep-11,governanceui | EP-09 | Given Governance & Executive UX, when add observability and audit hooks, then the deliverable is reviewed, tested, and demoable against the contract pack. | Frontend Engineer | Release 1
EP-11-ST-06 | Story | Governance & Executive UX: Integration and demo readiness | Integrate with dependent services and provide demo evidence. |  | EP-11 | EP-11 |  | Medium | 5 | Sprint 8 | GovernanceUI | story,ep-11,governanceui | EP-09 | Given Governance & Executive UX, when integration and demo readiness, then the deliverable is reviewed, tested, and demoable against the contract pack. | Frontend Engineer | Release 1
EP-11-TS-01 | Task | Governance & Executive UX: Test automation | Add unit, integration, and contract tests. |  | EP-11 | EP-11 | EP-11-ST-03 | High | 3 | Sprint 8 | GovernanceUI | task,qa,ep-11 | EP-11-ST-03 | Automated tests pass in CI for the scoped area. | QA Engineer | Release 1
EP-11-TS-02 | Task | Governance & Executive UX: Documentation | Write service README, runbook, and handoff notes. |  | EP-11 | EP-11 | EP-11-ST-03 | Medium | 2 | Sprint 8 | GovernanceUI | task,docs,ep-11 | EP-11-ST-03 | Documentation is complete and reviewed. | Tech Writer | Release 1
EP-12-ST-01 | Story | Hardening, Performance & Launch: Define contract and ADRs | Create detailed contracts, ADRs, and coding conventions for the area. |  | EP-12 | EP-12 |  | Critical | 3 | Sprint 10 | Hardening | story,ep-12,hardening | EP-08 | Given Hardening, Performance & Launch, when define contract and adrs, then the deliverable is reviewed, tested, and demoable against the contract pack. | Tech Lead | Release 1
EP-12-ST-02 | Story | Hardening, Performance & Launch: Implement service skeleton | Create service repository/module, health checks, config, and CI integration. |  | EP-12 | EP-12 |  | Critical | 5 | Sprint 10 | Hardening | story,ep-12,hardening | EP-08 | Given Hardening, Performance & Launch, when implement service skeleton, then the deliverable is reviewed, tested, and demoable against the contract pack. | Tech Lead | Release 1
EP-12-ST-03 | Story | Hardening, Performance & Launch: Implement primary endpoint or worker flow | Deliver the main functional path with tests and tracing. |  | EP-12 | EP-12 |  | Critical | 8 | Sprint 10 | Hardening | story,ep-12,hardening | EP-08 | Given Hardening, Performance & Launch, when implement primary endpoint or worker flow, then the deliverable is reviewed, tested, and demoable against the contract pack. | Tech Lead | Release 1
EP-12-ST-04 | Story | Hardening, Performance & Launch: Add policy, validation, and error handling | Add guardrails, validation, and standard error envelope behavior. |  | EP-12 | EP-12 |  | Critical | 5 | Sprint 10 | Hardening | story,ep-12,hardening | EP-08 | Given Hardening, Performance & Launch, when add policy, validation, and error handling, then the deliverable is reviewed, tested, and demoable against the contract pack. | Tech Lead | Release 1
EP-12-ST-05 | Story | Hardening, Performance & Launch: Add observability and audit hooks | Emit logs, traces, metrics, and audit events for the area. |  | EP-12 | EP-12 |  | Critical | 3 | Sprint 10 | Hardening | story,ep-12,hardening | EP-08 | Given Hardening, Performance & Launch, when add observability and audit hooks, then the deliverable is reviewed, tested, and demoable against the contract pack. | Tech Lead | Release 1
EP-12-ST-06 | Story | Hardening, Performance & Launch: Integration and demo readiness | Integrate with dependent services and provide demo evidence. |  | EP-12 | EP-12 |  | Critical | 5 | Sprint 10 | Hardening | story,ep-12,hardening | EP-08 | Given Hardening, Performance & Launch, when integration and demo readiness, then the deliverable is reviewed, tested, and demoable against the contract pack. | Tech Lead | Release 1
EP-12-TS-01 | Task | Hardening, Performance & Launch: Test automation | Add unit, integration, and contract tests. |  | EP-12 | EP-12 | EP-12-ST-03 | High | 3 | Sprint 10 | Hardening | task,qa,ep-12 | EP-12-ST-03 | Automated tests pass in CI for the scoped area. | QA Engineer | Release 1
EP-12-TS-02 | Task | Hardening, Performance & Launch: Documentation | Write service README, runbook, and handoff notes. |  | EP-12 | EP-12 | EP-12-ST-03 | Medium | 2 | Sprint 10 | Hardening | task,docs,ep-12 | EP-12-ST-03 | Documentation is complete and reviewed. | Tech Writer | Release 1
SPIKE-01 | Spike | Model route policy benchmark | Evaluate latency/cost tiers and route policy baselines. |  | EP-06 | EP-06 |  | High | 5 | Sprint 3 | ModelTool | spike,benchmark,modeltool | EP-03-ST-03 | Benchmark report produced with recommendation. | ML Engineer | Release 1
SPIKE-02 | Spike | Threat model workshop | Run threat modeling for workload identity, tool execution, and release flow. |  | EP-02 | EP-02 |  | High | 5 | Sprint 2 | Security | spike,security | EP-02-ST-02 | Threat model documented with remediation backlog. | Security Engineer | Release 1
SPIKE-03 | Spike | Load test design | Design load and chaos test scenarios for run orchestration and worker scaling. |  | EP-12 | EP-12 |  | Medium | 5 | Sprint 10 | Hardening | spike,performance | EP-05-ST-06 | Approved performance test plan exists. | SRE | Release 1
Note on A1: Jira CSV import: map External ID to your Jira external key field or keep as a reference column.
Note on E1: Epic Name is only populated on Epic rows. Use Epic Ref/Epic Link for story-task association.
Note on O1: Acceptance Criteria is written as importable plain text; convert to Jira checklist plugin format if desired.

## Dependencies
Dependency ID | From External ID | To External ID | Reason | Mitigation
DEP-01 | EP-03-ST-03 | EP-02-ST-03 | Run creation requires tenant/workload auth flows. | Deliver token service skeleton in Sprint 1 before integration.
DEP-02 | EP-05-ST-03 | EP-03-ST-03 | Swarm execution depends on TaskSpec contract and run state model. | Freeze TaskSpec contract before execution alpha.
DEP-03 | EP-06-ST-03 | EP-02-ST-04 | Tool and model access requires policy enforcement and grants. | Complete policy engine rules before beta.
DEP-04 | EP-08-ST-03 | EP-07-ST-06 | Promotion decisions require evaluation evidence. | Tie release gate to EvaluationReport availability.
DEP-05 | EP-10-ST-03 | EP-03-ST-03 | Studio UX depends on run and plan APIs being stable. | Use mocked contracts until backend v1 fields freeze.
DEP-06 | EP-11-ST-03 | EP-09-ST-05 | Governance surfaces depend on audit and observability payloads. | Provide query APIs and field-level docs by Sprint 8.

## Acceptance_Notes
Area | Definition of done
Control plane | Run lifecycle, state transitions, retries, and cancellation behave according to the contract pack with test evidence.
Execution plane | Workers can accept, execute, checkpoint, and complete tasks with trace and audit correlation.
Knowledge plane | Retrieval results are permission-aware, ranked, and traceable to source references.
Security | All privileged flows use short-lived tokens; no direct raw credential use in workers.
Release | Only signed, evaluated candidates can be promoted; rollback path is tested.
UI | Studio, Evaluation, and Release surfaces work against documented APIs without using undocumented fields.
Operations | Metrics, logs, traces, and audit data are visible in dashboards and incident workflows.